## Sheet1
Task ID | Description | Status | Issue
S9
FE-235 | As a manager, I want to be able to control the financial adjustments that employees make on a lead to ensure only permissible adjustments are made | User Testing | he process works well, but the figures seem to be out on both policy and transaction | MM(Need to fix it)
FE-253 | As a super user, I want to be able manage email signatures to automate the signature of manual and automated communications | User Testing | Can you clarify what the difference between the templating and signature list views are? Is the signature list just a 1Q of templates of type signature? The ‘add’ button on signature list doesn’t seem to work The row click doesn’t do anything on signature list - should it? How are the signatures chosen at run time when a communication is sent? | Nikitha---Row click issue is there.
FE-292 | FE-292 – Inbound Email – Test Plan | QA Testing | Need to discuss and fix it | Ravi
FE-213 | As an employee, I want to be able to discount the lead premium to offer a discount to the client | User Testing | Except XML merge rest is ready for QAhttps://www.screencast.com/t/kjxIM0thc6---- After qs auto Recalculation with update dvalue | MM
FE_237 | As a finance controller, I want direct to insurer to be a payment option so that the ledgers can be managed appropriately | User Testing | There needs to be a link between payment screen and transactions---MM
FE-243 | As a credit controller, I want customers to be able to pay for a policy by card using the customer portal to remove manually processing of card payments | User Testing |  | MM(Need to fix it)
FE-248 | As a credit controller, I want to be able to see a summary of aged creditors by age of debt to see our total outstanding | QA Testing | it is working with sample data--need to discuss how to test it. | Narender
FE-239 | As a finance member of staff, I want the system to create an invoice linked to transactions to be able to group multiple transactions in future | To do | There is no test plan
FE-278 | As an employee, I want to be able to adjust the admin fees for a lead to set the correct fees | QA Testing | (Need To discuss)In development | Need to check with Ravi
FE-300 | As an employee, I want to be able to rebate commission on the lead to offer a discount to the client | User Testing | For system quotes would show the details (sections, declines, referrals, endorsements)----API related work | MM
FE-294 | As an office administrator, I want an inbox of unassigned comms to be able to assign them | In development | 1.An icon for attachments if there were any (with a number next to it for number of attachments?)e. Link to open4. There should be a button/buttons to link this email to a policy or client5. You should be able to search for the client to link it to by ID or insured name6. Alternatively you should be able to search for the policy to link it to by policy reference or client insured name7. When selecting a policy to link it to, you should optionally be able to link it to a specific version. These should be listed with:a.Version numberb. Typec.Statusd. Effective datee. Expiry date8. There should be options to open the client/policy in a new window to further investigate if it | Need to check with Ravi
FE-222 | As an employee, I want to be notified of inbound communications to know when a new message is waiting | User Testing | Working/I think Link to open pending | Nikitha(Need it fix it)
FE-384 | My task' sorting | User Testing | Just waiting on the default sort | Nikitha(we will check once again
FE-389 | Today' button on datepicker not working | To do
Sprint Back log
FE-343 | Branching test | To do
Fe-372 | Add new team - caching issue with user assign | To do
FE-385 | Default manual quote reference and price to blank on renewal workflow | To do
Core Background tasks
FE-153 | QS field dependency extension of functionality | User Testing | Configurations screens are not there, we will Fully verify this task, once Fe-271 is working. we will check it along with and let you know. | MS
FE-264 | As a renewals manager, I want to create a renewal lead in batch for existing policies to start the renewal process | QA Testing | I have discussed with team, they told me, both filters (By default & All policies) are not possible. We will check with once again with team and let you know. This issue is already mentioned in the attached doc2.Issue2: Filter issue there, by default it is showing 2 months in the furure. When we search for more than two months, those policies are not showing in the list | MS
FE-271 | As a super user, I want to be able to manage automatic attachment rules to create logic for what is attached to emails | In development |  | MS
FE-158 | Create new field formats to be used in reports | In development
FE-285 | As a superuser, I want to be able to expose report filters for people to be able to customise the report by specific criteria | In development
FE-273 | As a superuser, I want to be able to group report results to make results easier to view | In development
FE-306 | Sendgrid integration | In development
FE-247 | As a broker, I want to be able to set the introducer for a lead to track the leads provided by an introducer | In development |  | MS
Sprint-10
FE-197 | As a superuser, I want to be able to create users to give staff access to the system | User Testing | 1.The popup should close and the user table should refresh showing the new 2.user& 2FA? 3.It allowing same userid multiple time4.it is not showing existing role----Pending | Nikitha(Need to Fix)
FE-206 | As a superuser, I want to be able to manage users to edit and remove staff according to changes | QA Testing | 1.2FA?.2. email address & User name both are same | Nikitha
FE-284 | As a superuser, I want to be able to create and manage teams to logically group users | QA Testing(In development) | Need to discuss | Nikitha
FE-71 | Create a configured API for PW integration | User Testing | Need to discuss | MM
FE-73 | Parse XML response | User Testing | Need to discuss | MM
FE-338 | List of standard fields that we need to have on QS to have MTA working using same QS | To do
FE-337 | Copy QS / MTA functionality verification with Sub Questions | To do
FE-198 | As an employee, I want to be able to create an MTA lead to record the potential of a change | QA Testing | Still in testing
FE-307 | As an employee, I want to be able to mark an MTA lead as closed to log that an MTA will not be going ahead | QA Testing
FE-275 | As an employee, I want to be able to dismiss or snooze notifications | In development |  | Narender
FE-290 | As an employee, I want to view my tasks and notifications to action them | To do
FE-393 | The public QS for lead confirmation should be branded | To do
Need | Add brand section to client and policy popups | User Testing |  | Nikitha
FE398 | Pass brand structure to email and document templating | To do
FE-399 | Duplicate renewal workflow to NB workflow | QA Testing | Transactions are working,we are checking full cycle | MM
FE-279 | As a user, I want to be able to schedule reports to be generated at a specific time with specific parameters in order to receive regular data from the system | To do
FE-400 | check steve data export - it has an issue and Steve not sure what (probably product related) | To do